## Active Construction Job
(Do Not Modify) Construction Job | (Do Not Modify) Row Checksum | (Do Not Modify) Modified On | Name | Job Number | Customer | City | State | Start Date | End Date | Primary Workload | Primary Workload Workers | Secondary Workload | Secondary Workload Workers
12409dbe-fc18-4d79-8de7-dbf41a1d7108 | 8MYagjHTI/8RTORsmPTA+lQwylRZWCFlRmvyKaH0UOntgASfB9z0n++LC829dr9rrMLfyefEgf/ntkZUEH+N8Q== | 2026-05-21 00:49 | Steel Frame Retrofit | US-10001 | Northgate Commercial Holdings | Atlanta | GA | 2026-07-06 | 2026-07-08 | Electrical | 2
4d3ad717-752a-46d5-890a-898ba7306dac | tM4qFUEIPzIkrIfxCGYby8icKmCCHjV7COyHWHlNFwVwiimFbfNSIlNCjkI0VVFXl+Vnl5G1lBzQSiRyhKDwoA== | 2026-05-21 02:04 | Tenant Suite Wiring | US-10002 | Summit View Properties | Atlanta | GA | 2026-07-07 | 2026-07-15 | Electrical | 1 | Carpentry | 1
35753e32-deae-4c28-8615-7a5f69d8b64b | rwvYBqCyr30BrWXCpgL7VetCNMYNeuAGWMJ1CnYxQSpX4CGTL2uSm3JNkgn4IJOWTihCkBOCT0jp4wQPmQ5zOw== | 2026-05-21 00:49 | Loading Dock Expansion | US-10003 | Crescent Ridge Development | Atlanta | GA | 2026-07-06 | 2026-07-08 | Plumbing | 2
f19fbf42-9062-4c80-96ea-59098bbae549 | wR/RPs/5yfRqNS6q0bGNtUqcTZi+vVFB4FcjT3sHJRHzoP8k5sY9Ra+uhRl9Fdr7dFgVnkVKb1mhMG918x1e7Q== | 2026-05-21 00:49 | Central Plant Upfit | US-10004 | Harborline Builders Group | Atlanta | GA | 2026-07-08 | 2026-07-10 | Plumbing | 1 | Welder | 1
a2f77a56-e3b2-4e3d-a6cc-074bbccc312e | SyqzYVTWUaXEw+XrCqpFCASD24M8BpRNvknM8q82iqcJgSx0OA+EeDmINvHhwr+/YqILJk017nTlZpACSAZPcA== | 2026-05-21 00:49 | Atrium Lighting Upgrade | US-10005 | Blue Meridian Ventures | Boston | MA | 2026-07-13 | 2026-07-15 | Electrical | 1
011b0722-2c61-4c50-9b3a-b3175130dbca | uPqkPRXD8JuLIsUN+JV/DQcR5FoDwiBHNFB4VJ4yKgPikuLcJ0TEfzV0aHJkbaNymfr7bAuFznMfsVhqKoOojg== | 2026-05-21 00:49 | Office Core Repipe | US-10006 | Pinnacle Square Partners | Boston | MA | 2026-07-14 | 2026-07-16 | Electrical | 1 | Carpentry | 1
5c32d120-314a-4e89-9b4f-800009b32991 | uOOV/5nT+tpowfovR6pixfl1Ulzfm5tNFSN7KLqNR+dRHCi61am/tr+jY6joBLaURjR82/NbwUBLKjj36HkflA== | 2026-05-21 00:49 | Parking Deck Framing | US-10007 | Riverfront Commerce Group | Boston | MA | 2026-07-13 | 2026-07-15 | Plumbing | 2
4dbfe018-b408-49cd-ad79-e7086ed3dded | gYP7NVmloP0SGa0x5Rx6KkybMIKPx1TeRwFE4+DWoT2iwTCC/gN9kHpuq4CL6NWNLuR0cVYW5V341GML+C7XJg== | 2026-05-21 00:49 | Mechanical Room Weldout | US-10008 | Keystone Urban Development | Boston | MA | 2026-07-15 | 2026-07-17 | Plumbing | 1 | Welder | 1
89f7ac86-f6ad-4c9d-af58-13fa1bf0c125 | Zca6dD003SsNAewIA4QSuFOlwL4DjhC5WDuS4Loxxxxs05+N3nuM5RVmzHTUoVS1XbgJi76Buo/DkvFFngEC+g== | 2026-05-21 00:49 | Retail Shell Buildout | US-10009 | Elm Street Commerce | Atlanta | GA | 2026-07-20 | 2026-07-22 | Electrical | 2
35683c20-6b7c-4d68-965e-211cd4bccb17 | eUawpUDKVTz+ojsdZfdr0vETYpmP0mfpfbPzeXSYj9LVcrRK5IKaP3t8MOKpFT6rlCGdHriIKxn5nxs3P1Szrw== | 2026-05-21 00:49 | Lobby Circuit Refresh | US-10010 | Granite Peak Properties | Boston | MA | 2026-07-21 | 2026-07-23 | Electrical | 1
efaeef9f-c89b-441d-94e0-5d9d4dc314a6 | gbS3EatswscTQsHB4lVR4+AxICog5nLOrjFFvzk5nz3urIl7cLOCy7v3ooOvtuYZzsQpmJvHmM1bW3GnSXGuAw== | 2026-05-21 00:49 | Warehouse Pipe Repair | US-10011 | Sunset Harbor Holdings | Atlanta | GA | 2026-07-20 | 2026-07-22 | Plumbing | 2
d7e30d83-54bf-42f9-b3f4-b1587759ed96 | GtPPCp8eze69gmj0SvTVxoClAv7Td+6pnijzPiNklhDB2usdUk0OZazxBzh5CAlLhZI1Sgm6oh6fByboWZRuhA== | 2026-05-21 00:49 | Roof Access Weldments | US-10012 | Copperline Commercial Group | Boston | MA | 2026-07-22 | 2026-07-24 | Plumbing | 1 | Welder | 1
7262df9d-b36a-44fa-9e85-cfb9ee757ed9 | ldCUANgbZWqMkgh0+yQuMrMuqHZQ10IChadavPzUYNwapKCb4OvAkwhEUDwN9SjF/6UuV6OZhsTMGwbVcnR84g== | 2026-05-21 00:49 | Commercial Facade Repair | US-10013 | Harborview District Partners | Atlanta | GA | 2026-07-27 | 2026-07-29 | Electrical | 2
e3cb3732-32a2-4163-a9e5-56a248652bc3 | FDj7amPOY/bzmjBxMIEYfy5q7yWkhrTQVOLAzQKnAaSdf36jltrv2+pZUBQJX036mHy1QCSusG/mGOrBb5sbCA== | 2026-05-21 00:49 | Backhouse Panel Install | US-10014 | Northstar Workplace Ventures | Boston | MA | 2026-07-28 | 2026-07-30 | Electrical | 1 | Carpentry | 1
c06286d3-970e-4c01-b647-8c58becb6b09 | dr7QnaSgbLKdtYPf1rovW3e5BNV4PTZQrQCcnshSyWzKELa005dRVNHocU/DZvYf/ZFy43KMy3Xl2VO7BkNhgA== | 2026-05-21 00:49 | Service Bay Carpentry | US-10015 | Monarch Gateway Properties | Atlanta | GA | 2026-07-27 | 2026-07-29 | Plumbing | 1
b035edcb-9cbb-4ea6-9f9f-de2da6c4b2c0 | a3IYNjQS6IamZdwfkGEI3PvaBem37Rn8ejwt+YM2yz+jMmWGjISP6XyVHcuXSNBmZjETVOzG+CDSila9AMl2KA== | 2026-05-21 00:49 | Utility Chase Fabrication | US-10016 | Lakeside Commercial Holdings | Boston | MA | 2026-07-29 | 2026-07-31 | Plumbing | 1 | Welder | 1
d10ce341-a654-f111-bec7-70a8a5acb27a | Zgj13hIOkQt2eSsJo3t5Zr7q+CF1abUeUGDd1FsXyeCzmMsqxnUV/HtFSV5RnlmIzbquZGrnlOfUdA1hAyszzQ== | 2026-05-21 01:18 | Substation Feeder Retrofit | US-10017 | Granite Field Contractors | Atlanta | GA | 2026-06-01 | 2026-06-04 | Electrical | 2
d30ce341-a654-f111-bec7-70a8a5acb27a | idOmQOmPihJOmVjK+RSpLWsJEXq+78UbJTMJ9Wcunqne8ApejQl3VxVhH8bWwDHJOFCbgg+MU7SJv2D6gkvqwg== | 2026-05-21 00:49 | Boiler Drain Rework | US-10018 | Redstone Industrial Group | Boston | MA | 2026-06-01 | 2026-06-03 | Plumbing | 1 | Welder | 1
d50ce341-a654-f111-bec7-70a8a5acb27a | VzKOB3mRmbkV9bowWu8JIbOMInbgNceiu/LX+mb8LwZKdtAspYj4F6tBAVHpoKtRdNUBT3H6Hc8U2xhUfhDgiA== | 2026-05-21 00:49 | Concourse Lighting Refresh | US-10019 | Union Station Properties | Atlanta | GA | 2026-06-04 | 2026-06-08 | Electrical | 1 | Carpentry | 1
d70ce341-a654-f111-bec7-70a8a5acb27a | AP2uo1qhgMUllzrTpFCRUOTG2cDYqeSzEysUG803GGeeg0F2n8oJ9DeZuuiRxpMRQT4JrzW87MQD9L1lanAMgw== | 2026-05-21 00:49 | Riser Valve Replacement | US-10020 | Bayfront Logistics Holdings | Boston | MA | 2026-06-04 | 2026-06-08 | Plumbing | 2
d90ce341-a654-f111-bec7-70a8a5acb27a | PBe4VeI4UHt05t+NuvYjemzr/kPNoaVRUDpm9Rrs15QuzzhWcaNkwH0Han6+MZSErMNJw4WhtlCPCwEjpIluAw== | 2026-05-21 01:18 | Switchgear Room Expansion | US-10021 | Ironline Commerce Partners | Atlanta | GA | 2026-06-09 | 2026-06-10 | Electrical | 2
4c5d84a2-a654-f111-bec7-7c1e5252fc61 | c08wOfm6IDyiOh7wsZ6eT4nzmO7I+CNnwl6nSaiY/k41a7xXmsY/EqAeVjVWamZpIYTAD9hk7f+8/EGuNQKKQw== | 2026-05-21 00:49 | Pump Header Tie-In | US-10022 | Horizon Point Developers | Boston | MA | 2026-06-09 | 2026-06-11 | Plumbing | 1 | Electrical | 1
dd0ce341-a654-f111-bec7-70a8a5acb27a | O9MPOzmoMb3JztCgeVOFQIgCGyj4JNErlOThfxqDeDjOgrw7LfuXuJLtLySHdC6a4VVLkFcnbLDdTqpi9Bh4aQ== | 2026-05-21 01:18 | Tenant Breaker Realignment | US-10023 | Oakridge Commercial Trust | Atlanta | GA | 2026-06-12 | 2026-06-18 | Electrical | 1
df0ce341-a654-f111-bec7-70a8a5acb27a | kT4EnGDjo606T8SP6Ov+SRFVyaKmXcNTYWoYA4EMBwrYRFxyNj57WBqzNIu/Im23B/eUJ5w1wS8f3mWMYVZWtQ== | 2026-05-21 00:49 | Chiller Loop Repipe | US-10024 | Beacon Harbor Capital | Boston | MA | 2026-06-12 | 2026-06-16 | Plumbing | 2 | Welder | 1
e10ce341-a654-f111-bec7-70a8a5acb27a | ddgNu7DImz9HLO2gnefgbFBL0ASBceIOOiqXVMMu+mxFPykIH2QvkMfcINRXQmQBp/hbCQ6d+0RQL2QN0lhClQ== | 2026-05-21 01:18 | Corridor Lighting Trimout | US-10025 | Lexington Urban Properties | Atlanta | GA | 2026-06-17 | 2026-06-22 | Electrical | 1 | Carpentry | 1
e30ce341-a654-f111-bec7-70a8a5acb27a | F5ouNSrRMRdQXRsLr+H1bmYOwn2cQgKwmTqsE/4WqRxRxniK4rlxCc416Xol0xOQHVSwzjyql3uiY5F99mtcyQ== | 2026-05-21 00:49 | Service Line Rebalance | US-10026 | Ridgeway Facilities Group | Boston | MA | 2026-06-17 | 2026-06-19 | Plumbing | 1
e50ce341-a654-f111-bec7-70a8a5acb27a | vnkimubpsCmsYUULqNw/9ikFowdKSKTFZ+rf/9X5U3aoOIcXsF8naoF2Eiy6TVxDyfTBsqFPt1KLo9U7tBmbRA== | 2026-05-21 01:18 | Generator Bus Upgrade | US-10027 | Anchorpoint Construction Group | Atlanta | GA | 2026-06-22 | 2026-06-25 | Electrical | 2
e70ce341-a654-f111-bec7-70a8a5acb27a | GiBdZ5AVbt+sQGxWSzJGatZ7wWV0kU0fGoT26PTFcNWPN3AKyHHR5wcUEKwg3OU5E3M07sby97uu379+/OirKw== | 2026-05-21 00:49 | Hydronic Weld Prep | US-10028 | North Harbor Developments | Boston | MA | 2026-06-22 | 2026-06-24 | Plumbing | 1 | Welder | 1
e90ce341-a654-f111-bec7-70a8a5acb27a | 0jqj/dSzH515EcvXPC+rIEtU6fscuOoP9zKNTA+9LjNsNWA9vceDjmAr4yc4oYyhjd7GNh64SOYc6e3xMwEWag== | 2026-05-21 01:18 | Panelboard Circuit Cleanup | US-10029 | Maple Street Ventures | Atlanta | GA | 2026-06-25 | 2026-06-30 | Electrical | 1
eb0ce341-a654-f111-bec7-70a8a5acb27a | NQAiyjMN6s9bwLj4LM1wiGyGZRpZpTisRXfsxtQt6FODWKuoV0wuEtnbbdB28+z6PTWUqHu7EDbqJCDrRPoCgA== | 2026-05-21 00:49 | Domestic Line Retrofit | US-10030 | Crosswind Property Group | Boston | MA | 2026-06-25 | 2026-06-29 | Plumbing | 2
ed0ce341-a654-f111-bec7-70a8a5acb27a | TH39c1IwqsrSXM7BCXEr85cJ0icGL+OvB4uWoY0YpHS/at6Ymuc0u/FgQo0MavCFiC43m4QcQQ2ZugvKZPdJ4Q== | 2026-05-21 01:18 | Stairwell Fixture Install | US-10031 | Mission Creek Holdings | Atlanta | GA | 2026-06-30 | 2026-07-01 | Electrical | 1 | Carpentry | 1
ef0ce341-a654-f111-bec7-70a8a5acb27a | bNahJN7DBsFhRVm9K8VN6/RzlJR+6iQEn3n+KiL68JdCg3sGnp8GL03jTE92GBpEHbBiaHQGpCv23cd2HKaNcw== | 2026-05-21 00:49 | Valve Rack Weldout | US-10032 | Portview Commercial Trust | Boston | MA | 2026-06-30 | 2026-07-02 | Plumbing | 1 | Welder | 1

## hiddenSheet (hidden)
md_constructionjob:824NAN9ktrVJPlqjmz0vspBlV8+xcU725ffOzmu7eEuPW32SU6l0m+TzJdhRZxNUNwB/KiDwJCXNPUFgtbAgbQ==:md_constructionjobid=%28Do%20Not%20Modify%29%20Construction%20Job&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&md_jobname=Name&md_jobnumber=Job%20Number&md_customername=Customer&md_city=City&md_state=State&md_startdate=Start%20Date&md_enddate=End%20Date&md_primaryworkload=Primary%20Workload&md_primaryworkloadworkers=Primary%20Workload%20Workers&md_secondaryworkload=Secondary%20Workload&md_secondaryworkloadworkers=Secondary%20Workload%20Workers
Electrical | Plumbing | Carpentry | Welder
Electrical | Plumbing | Carpentry | Welder